## Sheet1
Priority | Tasks Description | Estimated Effort (manday)
5 | As a user, I want to register an account in the application | 3
6 | As a user, I want to login in the application | 5
7 | As a user, I want to login with an external provider authentication (Facebook, Google) | 7
1 | As a user, I want to know my current location | 7
3 | As a user, I want to communicate with the application using Speech Recognition | 14
2 | As a user, I want to be able to navigate from my current location to a destination | 30
8 | As an administrator, I want to be able to login to the admin portal | 3
4 | As an administrator, I want to perform CRUD operations on Location, Facility, Unit, Beacon and Floor Plan | 14
6 | As an administrator, I want to view statistics of a user or unit | 14